## Sheet1
Meetings | 2016-01-12 | via Google hangout
Attendance | Jason
Li
Chris
Casey
Calub
[6 empty] | Main | Backup
Topics | Agreed on next meeting for Monday 18, for next progress check |  |  | Jobs | Jason | Manager | programming / design
| Agreed upon assigned jobs |  |  |  | Calub | Programming | Design/doncumentaiton
| Discussed meetings with client/Prof on 1/14/2016 |  |  |  | Li | Test | UI/documentation
| Discussed design and schedule |  |  |  | Casey | UI | Programming/documentaion
[5 empty] | Chris | Documantaion | programming/test/manager
Tasks | Database | Calub | 2016-01-17
| UI | Casey | 2016-01-17
| Use case drafts | Chris | 2016-01-14
| Test designs | Li | 2016-01-19
| Prepare for meeting | Jason | 2016-01-14