## Sheet1
Meetings | 2016-01-14 | In Deschutes Hall 354
Attendance | Prof/Client
Jason
Chris
Casey
[6 empty] | Main | Backup
Topics | Talk to client about address fields - Make sure it meets USPS standards |  |  | Jobs | Jason | Manager | programming / design
| Prof - Upload documents to website |  |  |  | Calub | Programming | Design/doncumentaiton
| Prof - Make timeline |  |  |  | Li | Test | UI/documentation
| Prof - Revision to use case needed |  |  |  | Casey | UI | Programming/documentaion
| Informed the Prof of switching programming envirements |  |  |  | Chris | Documantaion | programming/test/manager
Tasks | Use case revision | Chris | 2016-01-20
| Input requirements | Team | 2016-01-20
| Prepare preview to client | Team | 2016-01-20
| Upload docs to assembla | Jason/Chris | 2016-01-20
| Address other issues to ask | Team | 2016-01-20