## Sheet1
Meetings | 2016-01-19 | via Google handout (change in date and time do to team conflicts)
Attendance | Li
Jason
Chris
Casey
Calub
[6 empty] | Main | Backup
Topics | Talked about current state of the database and current known issues |  |  | Jobs | Jason | Manager | programming / design
| Redirecting team to fix swift issues to associate UI for client meeting on 1/20/2016 |  |  |  | Calub | Programming | Design/doncumentaiton
| Swift is assisting in testing and other features |  |  |  | Li | Test | UI/documentation
| Testing is complete by swift except UI that needs to be link to the database |  |  |  | Casey | UI | Programming/documentaion
| schedule next meeting for 1/26/2016 |  |  |  | Chris | Documantaion | programming/test/manager
Tasks | Use case revision | Chris | 2016-01-20
| Input requirements | Team | 2016-01-20
| Prepare preview to client | Team | 2016-01-20
| Upload docs to assembla | Jason/Chris | 2016-01-20
| Address other issues to ask | Team | 2016-01-20
| Database | Calub | 2016-01-19
| UI integration to database | Jason/Casey | 2016-01-19
| Testing UI | Li | 2016-01-21
| L1 complete 1/23/16 | Team | 2016-01-23