## Sheet1
Meetings | 2016-01-26 | via Google handout
Attendance | Li
Jason
Chris
Casey
[6 empty] | Main | Backup
Topics | Talked about current state of the database and current known issues |  |  | Jobs | Jason | Manager | programming / design
| Redirecting team to fix swift issues to associate UI for client meeting on 1/20/2016 |  |  |  | Calub | Programming | Design/doncumentaiton
| Swift is assisting in testing and other features |  |  |  | Li | Test | UI/documentation
| Testing is complete by swift except UI that needs to be link to the database |  |  |  | Casey | UI | Programming/documentaion
| schedule next meeting for 1/26/2016 |  |  |  | Chris | Documantaion | programming/test/manager
Tasks | Work on documents and presentation for Friday | Chris | 2016-01-28
| Working on Name issue and final program for Friday | Jason | 2016-01-28
| Continue Test cases and doc | Li | 2016-01-28
| Prepare for UI change with Name issue being resolved | Casey | 2016-01-28